## Outline WBS Template
Project Name | GamemasterScrawl (5)
1 | Planning
| 1.1 | Creating PDD
| 1.2 | Researching Socket Technology
| 1.3 | Researching Competitors in the Space
| 1.4 | Researching Browser Technology
| 1.5 | Researching backend Systems/Languages
| 1.6 | Researching 3-D libraries
2 | Analysis
| 2.1 | Determine User-base
| 2.2 | Utilize JS/HTML/CSS for front-end design
| 2.3 | Utilize C# for backend
| 2.4 | Determine minimum browser-specs required
2.5
2.6
2.7
2.8
2.9
3 | Design
| 3.1 | Make Initial Screen Mockups
| 3.2 | Make initial Logo Mockups
| 3.3 | Consult an expert (Calix Daulton, Graphical Designer) on above mockups
| 3.4 | Repeat above steps until satisfactory design created
| 3.5 | Design JSON file structures for storing data
4 | Implementation
| 4.1 | Implement Sockets
| 4.2 | Implement login
| 4.3 | Implement User Management
| 4.4 | Implement 3D viewer
| 4.5 | Implement Map Editor
| 4.6 | Implement token management
| 4.7 | Ensure updates are global and syncronized
5 | Testing
| 5.1 | Create realistic use cases/scenarios a user could encounter (IE, short campaigns)
| 5.2 | Run those scenarios to stress test and ensure the program can heandle them
6 | Integration
| 6.1 | Obtain a minimum of 1 computer and 2 monitors for Celebration of Scholarship
| 6.2 | Download executable from github onto this computer
| 6.3 | Run a basic demo of features (Possibly from test scenarios) during celebration of Scolarship
7 | Maintenance
| 7.1 | Project will be open-source, so other devs are able to fork off and make changes as they see fit
| 7.2 | I may provide systematic updates after a final launch. Undetermined at this time
7.3